## Hoja1
	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37	38	39	40	41	42	43	44	45	46	47	48	49	50	51	52	53	54	55	56	57	58	59	60	61	62	63	64
UC1 – Login and Registration (All Systems)				RA(6)						D(10)										I(6)					T(3)
UC2 – Event Management (Event Organizer & Server Application)													RA(7)							D(12)												I(11)											T(3)
UC3 – Open a particular event (Event Organizer & Server Application)																																RA(5)						D(8)								I(8)								T(2)
UC4 - Register for an event (Event Attendee & Server Application)																																																						RA(5)					D(6)
UC5 - Calendar management for events (Event Attendee & Server Application)																																							RA(7)							D(10)										I(8)								T(1)
UC6 - Perform queries (Event Attendee & Server Application)
UC7 – Generate reports (Event Manager & Server Application)
UC8 - Assign users to subjects (Event Manager & Server Application)
UC9 - Create certificates of attendance (Event Organizer & Server Application)
UC10- Request certificate (Event Attendee & Server Application)
UC11 - Evaluate event (Event Attendee & Server Application)
UC12 - Launch and manage queries (Event Organizer & Server Application)

	20								21								23								24								25								27								28								30
	NOVEMBER

	65	66	67	68	69	70	71	72	73	74	75	76	77	78	79	80	81	82	83	84	85	86	87	88	89	90	91	92	93	94	95	96	97	98	99	100	101	102	103	104	105	106	107	108	109	110	111	112	113	114	115	116	117	118	119	120	121	122	123	124	125	126	127	128
UC1 – Login and Registration (All Systems)
UC2 – Event Management (Event Organizer & Server Application)
UC3 – Open a particular event (Event Organizer & Server Application)
UC4 - Register for an event (Event Attendee & Server Application)	D(2)		I(7)							T(3)
UC5 - Calendar management for events (Event Attendee & Server Application)	T(1)
UC6 - Perform queries (Event Attendee & Server Application)													RA(5)						D(9)									I(8)								T(2)
UC7 – Generate reports (Event Manager & Server Application)
UC8 - Assign users to subjects (Event Manager & Server Application)							RA(2)		D(5)				I(3)			T(1)
UC9 - Create certificates of attendance (Event Organizer & Server Application)																									RA(6)						D(10)										I(9)									T(2)
UC10- Request certificate (Event Attendee & Server Application)																																															RA(3)			D(7)							I(6)					T(2)
UC11 - Evaluate event (Event Attendee & Server Application)
UC12 - Launch and manage queries (Event Organizer & Server Application)

	1								2								4								5								7								9								11								12
	DECEMBER

	129	130	131	132	133	134	135	136	137	138	139	140	141	142	143	144	145	146	147	148	149	150	151	152	153	154	155	156	157	158	159	160	161	162	163	164	165	166	167	168	169	170	171	172	173	174	175	176
UC1 – Login and Registration (All Systems)
UC2 – Event Management (Event Organizer & Server Application)
UC3 – Open a particular event (Event Organizer & Server Application)
UC4 - Register for an event (Event Attendee & Server Application)
UC5 - Calendar management for events (Event Attendee & Server Application)
UC6 - Perform queries (Event Attendee & Server Application)
UC7 – Generate reports (Event Manager & Server Application)																				RA(5)					D(11)	D(8)								I(9)									T(2)
UC8 - Assign users to subjects (Event Manager & Server Application)
UC9 - Create certificates of attendance (Event Organizer & Server Application)
UC10- Request certificate (Event Attendee & Server Application)
UC11 - Evaluate event (Event Attendee & Server Application)	RA(4)				D(10)										I(8)								T(3)
UC12 - Launch and manage queries (Event Organizer & Server Application)										RA(5)						D(8)								I(7)							T(2)

	15								16								18								19								21								22
	DECEMBER

	Teams						Role								Hours
	Group 3						Requirements and analysis								60
	Group 1						Desing								105
	Group 2						Implementation and testing								117